## Sheet1
1. Inception Phase |  | Timeline
| Project planning and evaluation. | 2d
| Requirements gathering. | 5d
| Define features the system must support. | 5d
| Identify the stakeholders who oversee the system use. | 1d
| Users and other applications (i.e. actors) that will interface with the system. | 1d
| Define framework to identify business rules. | 3d
| List the events that the system must be aware of and respond to. | 3d
| List the constraints and risks place on the project. | 3d
| Define product selection criteria. | 2d
| Define project management environment. | 1d
| Prepare and obtain approval of sponsors for project mandate and approach. | 1d
| Define data warehouse objectives. | 4d
| Define query library/location matrix. | 2d
| Define query libraries. | 5d
| Establish meta-data. | 5d
| Prepare migration specifications. | 3d
| Develop query usage monitoring. | 5d
| Technical infrastructure assessment. | 5d
| Current technology assessment. | 3d
| Release of RFP. | 2d
The project plan must also place importance to:
Change control.
Risk assessment.
Training.
Scope agreements.
Resources.
Communication.
2. Elaboration Phase
| Review of RFPs and selecting winning candidate. | 1d
| Determine size of the data warehouse. | 3d
| Determine complexity and cleanliness of the data. | 4d
| Identify number of source databases and their characteristics. | 4d
| Select DSS tools. | 3d
| Determine network requirements. | 4d
| Conduct training. | 5d
| Integration of data. | 5d
| Plan quality assurance testing procedures. | 8d
3. Construction Phase
| Implement components. | 25d
| Systems integration. | 10d
| Conduct testing. | 10d
| Plan deployment. | 5d
| Develop support material. | 5d
4. Transitions Phase
| Roll-out of modules. | 3d
| Managing change-control requests. | 8d
| Conduct beta testing to validate the new system against user expectations. | 8d
| Perform converting operational databases. | 5d
| Evaluate performance and benchmarking. | 5d
| Evaluate that deployment baselines are complete. | 5d
| Obtain stakeholder feedback on deployment baselines consistency with evaluation criteria. | 3d
| Fine-tune product based on feedback. | 5d
| Release product to users. | 3d
| Product release milestones. | 5d